## RTM
REQUIREMENT TRACEABILITY MATRIX
Project Name: | Smart EV Charging and Navigation Management System | Created On: | 05-Oct-2023 | Reviewed On: | 07-Oct-2023
Release No: | v1.0 | Created By: | Development Team | Reviewed By: | Supervisor
Version: | EV-2.0 | Document: | Project Final Report V 1.54
ID | Requirement ID | Requirement Description | Use Case ID | Sequence Diagram | Test Case ID | UI ID | Tested on / Verified | Tested By
1 | FR-1 | System shall allow users to register an account using email and password | UC-01 | SD-01 | TC-01 | UI-03 | Verified | Asad, Zoya
2 | FR-2 | System shall allow registered users to login using valid credentials | UC-01 | SD-01 | TC-01 | UI-03 | Verified | Asad, Zoya
3 | FR-3 | System shall allow authenticated users to logout from the system | UC-01 | SD-02 | TC-01 | UI-03 | Verified | Asad, Zoya
4 | FR-4 | System shall allow users to reset their password via registered email | UC-01 | SD-02 | TC-01 | UI-03 | Verified | Asad, Zoya
5 | FR-5 | System shall allow authenticated users to change their account password | UC-02 | SD-03 | TC-01 | UI-13 | Verified | Asad, Zoya
6 | FR-6 | System shall display nearby charging stations based on user's current GPS location | UC-04 | SD-04 | TC-02 | UI-04 | Verified | Zoya, Waleed
7 | FR-7 | System shall display station details: name, charger type, price per kWh, and availability | UC-05 | SD-05 | TC-02 | UI-04 | Verified | Zoya, Waleed
8 | FR-8 | System shall allow users to filter charging stations by geographic location | UC-04 | SD-04 | TC-02 | UI-04 | Verified | Zoya, Waleed
9 | FR-9 | System shall allow users to filter stations by charger compatibility (AC / DC) | UC-04 | SD-04 | TC-02 | UI-04 | Verified | Zoya, Sarwat
10 | FR-10 | System shall allow users to filter stations by maximum charging cost per kWh | UC-04 | SD-04 | TC-02 | UI-04 | Verified | Zoya, Sarwat
11 | FR-11 | System shall allow users to search charging stations by name, city, or area | UC-04 | SD-04 | TC-02 | UI-04 | Verified | Zoya, Sarwat
12 | FR-12 | System shall provide turn-by-turn directions from user location to selected station | UC-06 | SD-06 | TC-03 | UI-07 | Verified | Waleed, Zoya
13 | FR-13 | System shall allow users to set a start location for route planning via GPS or map tap | UC-06 | SD-06 | TC-03 | UI-07 | Verified | Waleed, Zoya
14 | FR-14 | System shall allow users to enter a destination point for route planning | UC-06 | SD-06 | TC-03 | UI-07 | Verified | Waleed, Zoya
15 | FR-15 | System shall allow users to input current vehicle battery percentage before planning | UC-06 | SD-06 | TC-03 | UI-07 | Verified | Waleed, Zoya
16 | FR-16 | System shall calculate and display charging stations within the vehicle's travel range | UC-06 | SD-06 | TC-03 | UI-07 | Verified | Waleed, Zoya
17 | FR-17 | System shall notify the user when no charging station is available within remaining range | UC-06 | SD-06 | TC-03 | UI-07 | Verified | Waleed, Zoya
18 | FR-18 | System shall allow EV owners to add multiple vehicle profiles to their account | UC-03 | SD-03 | TC-04 | UI-05 | Verified | Zoya, Sarwat
19 | FR-19 | System shall allow EV owners to view a list of all saved vehicle profiles | UC-03 | SD-03 | TC-04 | UI-05 | Verified | Zoya, Sarwat
20 | FR-20 | System shall allow EV owners to edit existing vehicle profile information | UC-03 | SD-03 | TC-04 | UI-05 | Verified | Zoya, Sarwat
21 | FR-21 | System shall allow EV owners to delete vehicle profiles with confirmation prompt | UC-03 | SD-03 | TC-04 | UI-05 | Verified | Zoya, Sarwat
22 | FR-22 | System shall allow users to select a saved vehicle profile for route planning | UC-03 | SD-03 | TC-04 | UI-07 | Verified | Waleed, Zoya
23 | FR-23 | System shall display and compare charging costs from multiple available stations | UC-05 | SD-05 | TC-05 | UI-04 | Verified | Waleed, Zoya
24 | FR-24 | System shall estimate total charging cost based on station pricing and battery capacity | UC-05 | SD-05 | TC-05 | UI-04 | Verified | Waleed, Zoya
25 | FR-25 | System shall allow station owners to register and login to a dedicated portal | UC-14 | SD-14 | TC-06 | UI-08 | Verified | Sarwat, Asad
26 | FR-26 | System shall allow station owners to register a new charging station with full details | UC-15 | SD-15 | TC-06 | UI-09 | Verified | Sarwat, Asad
27 | FR-27 | System shall allow station owners to update charging station information | UC-17 | SD-17 | TC-06 | UI-09 | Verified | Sarwat, Asad
28 | FR-28 | System shall allow station owners to update station availability status in real-time | UC-17 | SD-17 | TC-06 | UI-09 | Verified | Sarwat, Asad
29 | FR-29 | System shall allow station owners to view session history and usage reports | UC-16 | SD-16 | TC-06 | UI-08 | Verified | Sarwat, Asad
30 | FR-30 | System shall allow station owners to manage individual charger units at their station | UC-15 | SD-15 | TC-06 | UI-09 | Verified | Sarwat, Asad
31 | FR-31 | System shall allow station owners to view their personal account profile | UC-16 | SD-16 | TC-06 | UI-13 | Verified | Sarwat, Asad
32 | FR-32 | System shall allow administrators to add new charging station records to the system | UC-11 | SD-11 | TC-08 | UI-11 | Verified | Asad, Sarwat
33 | FR-33 | System shall allow administrators to update existing charging station information | UC-11 | SD-11 | TC-08 | UI-11 | Verified | Asad, Sarwat
34 | FR-34 | System shall allow administrators to view a complete list of all charging stations | UC-11 | SD-11 | TC-08 | UI-11 | Verified | Asad, Sarwat
35 | FR-35 | System shall allow administrators to delete charging station records | UC-11 | SD-11 | TC-08 | UI-11 | Verified | Asad, Sarwat
36 | FR-36 | System shall allow administrators to add new vehicle model data to the system | UC-13 | SD-13 | TC-08 | UI-10 | Verified | Asad, Sarwat
37 | FR-37 | System shall allow administrators to update existing vehicle model data | UC-13 | SD-13 | TC-08 | UI-10 | Verified | Asad, Sarwat
38 | FR-38 | System shall allow administrators to view all vehicle records in the system | UC-13 | SD-13 | TC-08 | UI-10 | Verified | Asad, Sarwat
39 | FR-39 | System shall allow administrators to delete vehicle records with confirmation | UC-13 | SD-13 | TC-08 | UI-10 | Verified | Asad, Sarwat
40 | FR-40 | System shall allow administrators to view all registered user accounts | UC-09 | SD-09 | TC-08 | UI-12 | Verified | Asad, Sarwat
41 | FR-41 | System shall allow administrators to update user account information | UC-09 | SD-09 | TC-08 | UI-12 | Verified | Asad, Sarwat
42 | FR-42 | System shall allow administrators to activate or deactivate user accounts | UC-09 | SD-09 | TC-08 | UI-12 | Verified | Asad, Sarwat
43 | FR-43 | System shall allow administrators to permanently delete user accounts | UC-09 | SD-09 | TC-08 | UI-12 | Verified | Asad, Sarwat
44 | FR-44 | System shall allow administrators to approve or reject newly submitted charging stations | UC-10 | SD-10 | TC-08 | UI-11 | Verified | Asad, Sarwat
45 | FR-45 | System shall allow EV owners to submit star ratings (1–5) for charging stations | UC-07 | SD-07 | TC-09 | UI-04 | Verified | Zoya, Sarwat
46 | FR-46 | System shall allow EV owners to submit written text reviews for charging stations | UC-07 | SD-07 | TC-09 | UI-04 | Verified | Zoya, Sarwat
47 | FR-47 | System shall display overall ratings and all user reviews for each charging station | UC-07 | SD-07 | TC-09 | UI-04 | Verified | Zoya, Sarwat
48 | FR-48 | System shall allow administrators to identify and remove inappropriate or spam reviews | UC-12 | SD-12 | TC-09 | UI-10 | Verified | Asad, Sarwat
49 | FR-49 | System shall display available amenities (Wi-Fi, Parking, Café, Restroom) for each station | UC-05 | SD-05 | TC-10 | UI-14 | Verified | Zoya, Sarwat
50 | FR-50 | System shall allow station owners to update the list of available amenities at their station | UC-17 | SD-17 | TC-10 | UI-09 | Verified | Sarwat, Asad
51 | FR-51 | System shall allow users to filter stations based on required amenities | UC-04 | SD-04 | TC-10 | UI-15 | Verified | Zoya, Sarwat